## Gant Diagram
Task ID | Task | Dependencies | Reponsible | Days
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1.01 | Create login mockups |  | Alejandro
1.02 | Changes to Login Muckups | 1.01 | Javier
1.03 | Develop the login interface based on the Muckups | 1.02 | Cesar | bar: Days 2 to Days 3
1.04 | Create necessary fields and tables in the Datalight DB |  | Moises
1.05 | Program the operation of the login form | 1.03 | Javier | bar: Days 4 to Days 5
1.06 | Develop data entry validations | 1.05 | Alejandro | bar: Days 5
1.07 | Validate correct operation in different different access terminals and credentials | 1.03-1.06 | Cesar | bar: Days 6 to Days 7
2.01 | Create mockup of the topic creation interface |  | Alejandro
2.02 | Apply changes to create topic mockups | 2.01 | Javier
2.03 | Develop the interface of the creation of typicals based on the muckups | 2.02 | Cesar | bar: Days 2 to Days 3
2.04 | Create fields and tables in the Datalight DB |  | Moises | bar: Days 1 to Days 2
2.05 | Program the required data form | 2.03 | Javier | bar: Days 4 to Days 5
2.06 | Data entry validation in the form | 2.05 | Alejandro | bar: Days 5
2.07 | Test of creation of topics in different terminals and different credentials | 2.03-2.06 | Moises | bar: Days 6 to Days 7

## Sprint 1
| Project Name: | DataLigth
| Product Owner: | Moises Mancilla Mora
| Project Mannager: | Arredondo Bonilla Cesar
1
8 Hrs = 1 Day
| Sprint Duration | 10 |  |  | Effort | Remaining in the following days ...
| Trend calculated in the last | 10 | Total Days |  | 59 | 59 | 33 | 24 | 16 | 12 | 7
| Task rows | 14 | Done days | 6 |  | 59 | 53.1 | 47.2 | 41.3 | 35.4 | 29.5 | 23.6 | 17.7 | 11.8 | 5.9
| Warning! These are necessary |  | Trend |  |  | 48.8095 | 39.3524 | 29.8952 | 20.4381 | 10.981 | 1.5238
| template rows |  | Trend Days | 6 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task ID | Task | History ID | Reponsible | Status | Est. | 48.8095 1: 1; 39.3524 2: 2; 29.8952 3: 3; 20.4381 4: 4; 10.981 5: 5; 1.5238 6: 6; 1.5238 7: 7; 1.5238 8: 8; 1.5238 9: 9; 1.5238 10: 10
1.01 | Create login mockups | E1H03 | Alejandro | To Do | 4 | 48.8095 1: 4; 39.3524 2: 0; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.02 | Changes to Login Muckups | E1H03 | Javier | Done | 2 | 48.8095 1: 2; 39.3524 2: 0; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.03 | Develop the login interface based on the Muckups | E1H03 | Cesar | To Do | 7 | 48.8095 1: 7; 39.3524 2: 4; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.04 | Create necessary fields and tables in the Datalight DB | E1H03 | Moises | Done | 5 | 48.8095 1: 5; 39.3524 2: 0; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.05 | Program the operation of the login form | E1H03 | Javier | Done | 6 | 48.8095 1: 6; 39.3524 2: 6; 29.8952 3: 6; 20.4381 4: 2; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.06 | Develop data entry validations | E1H03 | Alejandro | In Progress | 2 | 48.8095 1: 2; 39.3524 2: 2; 29.8952 3: 2; 20.4381 4: 2; 10.981 5: 2; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
1.07 | Validate correct operation in different different access terminals and credentials | E1H03 | Cesar | In Progress | 3 | 48.8095 1: 3; 39.3524 2: 3; 29.8952 3: 3; 20.4381 4: 3; 10.981 5: 3; 1.5238 6: 3; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.01 | Create mockup of the topic creation interface | E1H03 | Alejandro | Done | 4 | 48.8095 1: 4; 39.3524 2: 0; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.02 | Apply changes to create topic mockups | E2H01 | Javier | To Do | 2 | 48.8095 1: 2; 39.3524 2: 0; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.03 | Develop the interface of the creation of typicals based on the muckups | E2H01 | Cesar | To Do | 6 | 48.8095 1: 6; 39.3524 2: 3; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.04 | Create fields and tables in the Datalight DB | E2H01 | Moises | To Do | 5 | 48.8095 1: 5; 39.3524 2: 2; 29.8952 3: 0; 20.4381 4: 0; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.05 | Program the required data form | E2H01 | Javier | In Progress | 6 | 48.8095 1: 6; 39.3524 2: 6; 29.8952 3: 6; 20.4381 4: 2; 10.981 5: 0; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.06 | Data entry validation in the form | E2H01 | Alejandro | To Do | 3 | 48.8095 1: 3; 39.3524 2: 3; 29.8952 3: 3; 20.4381 4: 3; 10.981 5: 3; 1.5238 6: 0; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0
2.07 | Test of creation of topics in different terminals and different credentials | E2H01 | Moises | To Do | 4 | 48.8095 1: 4; 39.3524 2: 4; 29.8952 3: 4; 20.4381 4: 4; 10.981 5: 4; 1.5238 6: 4; 1.5238 7: 0; 1.5238 8: 0; 1.5238 9: 0; 1.5238 10: 0